Roadworks - Contaminated Soil Management Procedure

(Including management of coastal acid sulphate soils, i.e. Coode Island silt)

City of Melbourne

April 2023

Table of Contents

1.0	Introduction	3

1.1	Objective	3

1.2	Scope of the Procedure	3

2.0	Underlying principles	4

3.0	Victorian waste management statutory requirements	4

3.1	Environment Protection Act 1970	4

3.2	Industrial Waste Management Policy (Waste Acid Sulfate Soils)	4

3.2.1	Victorian Best Practice Guidelines for Assessing and Managing Coastal Acid Sulfate Soils	4

3.3	Environment Protection (Industrial Waste Resource) Regulations 2009	5

3.3.1	Industrial Waste Resource Guidelines	6

3.3.2	Transport and Disposal	7

3.3.3	Exemptions	7

3.4	Asbestos Removal from Soil	7

4.0	Soil management procedures	8

4.1	Step 1 – Project Planning	8

4.2	Step 2 - Excavation	13

4.3	Step 3 – Disposal	14

4.3.1	Transport Requirements	16

4.3.2	Disposal Requirements	16

4.3.3	Material Tracking	17

5.0	Implementation plan	18

5.1	Overview	18

5.2	Training	18

5.3	Roles and Responsibilities	19

5.3.1	Council	19

5.3.2	Contractor Responsibilities	19

5.3.3	Environmental Consultant (if required)	19

5.4	Procedure Auditing and Monitoring	20

5.5	Non-Conformance	20

6.0	Procedure review and updates	21

7.0	appendices	22

# Introduction

The City of Melbourne includes a number of areas where reclamation of low lying land coincided with early industrial activities, such as gasworks, abattoirs and tanneries. Waste products from these industrial activities were frequently used as fill or foundation material during redevelopment works, and thus contaminated soils are likely to be present in these areas of inner urban Melbourne. In fact, there have been several instances in the past where contractors have encountered contaminated soil during road and subsurface service infrastructure repair and maintenance works within the City of Melbourne. Similarly, the City of Melbourne is in an area that contains Coastal Acid Sulfate Soils which occur naturally along many parts of Victoria's coast.  When Coastal Acid Sulfate Soils are disturbed they can react with oxygen to produce sulfuric acid. This can result in environmental impacts; including acidification of water and soil, de-oxygenation of water, poor water quality, dissolution of metals from soil and corrosion of concrete and metal structures.

Such incidents have the potential to result in additional costs, work stoppage and/or delays, unexpected additional costs, and potential human exposure to contaminated soil. Excess contaminated soils and/or Coastal Acid Sulfate Soils, which are generated during infrastructure projects, must be managed in accordance with Victorian regulatory requirements.

## Objective

This Procedure aims to achieve the following objectives:

Summarise the regulatory requirements for managing contaminated soil and Coastal Acid Sulfate Soils in Victoria.

Provide Council with a Procedure for managing contaminated soil and Coastal Acid Sulfate Soils, which takes into account the nature and scale of works undertaken by the Council and its Contractors.

Provide a Procedure that supports more efficient management of contaminated soils and Coastal Acid Sulfate Soils, and which is cost effective and can be readily implemented by Council and its Contractors.

Develop an implementation plan for adoption of the proposed Procedure.

## Scope of the Procedure

This Procedure is intended to cover works by Council within road reserves.

The scope of this Procedure will address soil contamination and Coastal Acid Sulfate Soils, but will not address any other issues that may be associated with Council’s earthworks, such as management, disposal and reuse of other waste material (e.g. solid inert waste, bitumen, concrete), groundwater and surface water contamination, cultural heritage, or fauna and flora impacts.

This Procedure outlines the following:

Underlying principles (Section 2.0);

Victorian waste management statutory requirements (Section 3.0);

Soil management procedures (Section 4.0); and

Implementation plan (Section 5.0).

# Underlying principles

The Procedure is:

- Based on consideration of the nature and scale, and potential risks associated with Council’s infrastructure works;

- Cost effective; and

- Able to be readily implemented by Council and its Contractors.

# Victorian waste management statutory requirements

This section outlines the statutory framework that governs the management of contaminated soils in Victoria.

## Environment Protection Act 1970

The Environment Protection Act 1970 (the Act) is the primary legislation in Victoria for the protection of the environment.  It considers all aspects of environment (air, water, land, waste and noise). The Act aims to prevent pollution and environmental damage by enabling the establishment of environmental quality objectives and supporting implementation programs. The Act has been amended considerably since its inception in 1970, and incorporates a wide variety of mechanisms, enforcement measures and enables the development of many supporting subordinate instruments.

Principles consistent with the National Strategy on Ecologically Sustainable Development and the Intergovernmental Agreement on the Environment have been incorporated into the Act to assist with implementation and decision making.

## Industrial Waste Management Policy (Waste Acid Sulfate Soils)

An acid sulfate soil is any soil, sediment, unconsolidated geological material or disturbed consolidated rock mass, which contains metal sulfides exceeding criteria published by the Environment Protection Authority.  Waste acid sulfate soils and rock must be managed in accordance with the requirements of the Industrial Waste Management Policy (IWMP) (Waste Acid Sulfate Soils) (WASS) 1999. This policy provides a management framework and specific requirements for the management of acid sulfate soils in an environmentally responsible manner. The IWMP (WASS) requires that off-site disposal or reuse of waste acid sulfate soil may only occur at premises:

- that are licensed to dispose of that type of waste under the Environment Protection Act 1970; or

- where an EMP, prepared in accordance with the Policy, has been approved by the Authority.

The IWMP (WASS) also requires that onsite management of waste acid sulfate soil takes place where best practice environmental management guidelines (Victorian Best Practice Guidelines for Assessing and Managing Coastal Acid Sulfate Soils) are implemented.

### Victorian Best Practice Guidelines for Assessing and Managing Coastal Acid Sulfate Soils

The Victorian Best Practice Guidelines for Assessing and Managing Coastal Acid Sulfate Soils (BPMG) have been produced to guide landowners, developers and planners through an approach to assist them to make decisions about the assessment and management of Coastal Acid Sulfate Soils.

The Coastal Acid Sulfate Soils risk identification process in the BPMG is designed to guide a decision-making process for development or activity proposed on land that has been identified as having the potential to contain Coastal Acid Sulfate Soils.

The BPMG describes the following risk identification and assessment process;

- Stage A: Preliminary Coastal Acid Sulfate Soils hazard assessment.

- Stage B: Detailed site soil sampling program and assessment.

- Stage C: Surface/ground water sampling program and assessment.

- Stage D: Coastal Acid Sulfate Soils hazard assessment.

The impacts of disturbing Coastal Acid Sulfate Soils will vary between sites and the nature of activities.  The need to undertake detailed soil sampling an analysis will be dependent on the outcome of the preliminary Coastal Acid Sulfate Soils hazard assessment. The preliminary Coastal Acid Sulfate Soils hazard assessment is intended to take into account if the:

- activity is “High Risk”; and

- activity is to occur in a Coastal Acid Sulfate Soils risk area.

High Risk activities as described in the BPMG have been incorporated into the procedure (Section 4.1).  A map, based on publicly available information showing Coastal Acid Sulfate Soils Risk areas in the City of Melbourne has been developed and forms part of the Procedure (APPENDIX A).

## Environment Protection (Industrial Waste Resource) Regulations 2009

Hazardous wastes are sometimes generated as a result of activities such as the manufacturing of motor vehicles, paint and plastics, dry cleaning services, fast food outlets, dental surgeries and hospitals, and the remediation of contaminated land. In the Victorian statutory framework for environment protection, such wastes are referred to as Prescribed Industrial Waste. As these wastes pose a potentially higher risk to people and the environment, they are more closely regulated than other forms of waste.

The Environment Protection (Industrial Waste Resource) Regulations 2009 (the Regulations) are intended to manage Prescribed Industrial Waste within a risk-based regulatory system. The primary purpose of introducing this risk-based approach is to enable enhanced reuse and recycling of industrial waste resources in accordance with the waste hierarchy (shown in Figure 1) and to reinforce the safe management of Prescribed Industrial Waste by supporting the treatment of waste to reduce its hazard prior to disposal.

Figure 1: Waste Hierarchy (Sourced from the Victorian Environment Protection Authority, www.epa.vic.gov.au)

Under the framework established by the Regulations, industrial wastes are subject to hazard categorisation. Wastes are categorised on the basis of the potential hazard posed by their chemical composition or physical attributes, and those that are identified as Category A, B or C wastes, are regulated as Prescribed Industrial Waste. Less hazardous waste that falls below the Category C threshold is managed as industrial waste, or as fill material in the case of soils.

The Act and the Regulations place particular requirements on the management of Prescribed Industrial Waste, including:

- Obligations for generators to classify waste;

- Requirements for Prescribed Industrial Waste to be transported in Victorian Environment Protection Authority permitted vehicles;

- Requirement that Prescribed Industrial Waste can be sent only to Environment Protection Authority licenced facilities; and

- Tracking of waste from point of generation to final disposal.

### Industrial Waste Resource Guidelines

The Environment Protection Authority Industrial Waste Resource Guidelines (IWRG) 2009 provides guidance on compliance with the Regulations for the classification of waste soil.

Where a site has potentially contaminated soil, the soil must be assigned a hazard category of A, B, C or fill material prior to off-site reuse, or disposal.

Environment Protection Authority Guidance states that soils are considered potentially contaminated if they:

- Have been mixed with any wastes;

- Consist of, or partially consist of, soil of unknown origin that has been brought onto a site;

- Arise from sites where former uses include industrial, commercial, mining or agricultural activities; or,

- Have had manufactured chemicals applied.

Due to the widespread use of waste products from industrial activities to infill low lying areas, or as foundation material during redevelopment works, contaminated soils (as a result of mixing with waste) are likely to be present in areas of inner urban Melbourne.

Sampling and classification must be undertaken in accordance with Environment Protection Authority Publications Soil Sampling (‘IWRG702’) and Soil Hazard Categorisation and Management (‘IWRG621’).

The initial step in waste characterisation is to conduct a Preliminary Site Investigation (PSI) in accordance with Australian Standard 4482.1. The primary objectives of the PSI are to:

- Assess the potential for the soil to be contaminated; and

- Identify which contaminants require analysis to determine the appropriate hazard category.

Where a PSI identifies that the soil is likely to be contaminated, the Guidelines require the analysis to be for all chemical substances known, and reasonably expected to be present in the waste. In the event that a site history assessment is not undertaken, or not known, and in particular where information indicates a high likelihood that contaminated soil is likely to be present, then a conservative position should be adopted, typically involving testing the broad range of chemicals listed in Table 2 of Environment Protection Authority Publication IWRG621.

Environment Protection Authority Publication IWRG621 also provides threshold values to categorize soil into one of four hazard classes:

- Category A - Highest waste classification.  This soil must be treated prior to disposal as there are no landfills licensed to receive Category A waste in Victoria.

- Category B - This soil can be treated or disposed to landfill.

- Category C - This soil can be treated or disposed to landfill.

- Fill Material - Lowest waste classification. Provided it is safe to do so (based on consideration of the State Environment Protection Policy (Prevention and management of Contamination of Land)) this soil can be reused on other sites or disposed to landfill.  Fill material includes rock of naturally occurring materials.

Soil that contains asbestos, or Asbestos Containing Material, but no other chemical contamination is classed as Category C Asbestos Waste to be disposed to a landfill, licensed to accept this waste. Such material must be removed, packaged, transported and disposed of in accordance with Environment Protection Authority and Worksafe Victoria requirements.

### Transport and Disposal

Category A, B or C soils and Asbestos Waste are Prescribed Industrial Waste under the Environment Protection (Industrial Waste Resource) Regulations 2009. Transport and disposal of Prescribed Industrial Waste is required to be carried out using vehicles permitted by Environment Protection Authority to carry such materials, and must be tracked using Environment Protection Authority Waste Transport Certificates.  The transport of waste Coastal Acid Sulfate Soils does not require use of transported certificates or permitted vehicles.

Asbestos from industrial origins (including commercial or trade activities) must be transported and disposed in accordance with the guidelines in Environment Protection Authority Publication IWRG611 Asbestos Transport and Disposal.

Landfills must be licenced by Environment Protection Authority to receive Prescribed Industrial Waste and asbestos. The landfills will have in place their own processes and procedures to assess the material being received.

### Exemptions

A waste transporter, transporting Prescribed Industrial Waste for no fee or reward, where the net load is less than 50 kg or litres is exempted from the requirement to hold a transport permit under section 53A of the Act and the requirements to use transport certificates.

## Asbestos Removal from Soil

Environment Protection Authority and Worksafe Victoria have developed a Guidance Note – Asbestos Contaminated Soil (Guidance Note) to assist in understanding statutory obligations regarding assessment of soil contaminated with Asbestos Containing Material. The Guidance Note is intended to clarify measures for removing Asbestos Containing Material from soil prior to disposal of the Asbestos Containing Material and residual soil. The Guidance Note describes;

- Who should inspect asbestos contaminated soil;

- Who can remove asbestos contamination from soil;

- Requirements relating to transportation and disposal of asbestos contaminated soil (see also Section 3.2.2); and,

- Suggested means of documenting assessment outcomes.

The assessment of Asbestos Containing Material contaminated soil and removal of Asbestos Containing Material from soil should be in accordance with this Guidance Note.

# Soil management procedures

The Procedure is divided into the following three steps and the management procedures to be followed in each step are described in Sections 4.1 to 4.3.

- Step 1 – Project Planning (including Coastal Acid Sulfate Soils screening)

- Step 2 – Excavation

- Step 3 – Disposal

There are a number of different scenarios in each step, and the Council and its Contractors can determine which scenario is applicable for a respective project by following the decision making flow chart provided in Appendix B.

## Step 1 – Project Planning

The decision making process and procedures to be followed in this step are summarised as follows:

- Council proposes an infrastructure project.

- Council assesses the likelihood that Coastal Acid Sulfate Soils will be disturbed during the project.

- Council assesses the project scope of works to determine if soils will be excavated.

- If soils will be excavated during the works, the project design should be assessed to determine if it is possible to reuse soils as part of the works, to prevent the generation of excess soils.

- If excess soils will be generated during the works, then the project should be reassessed to determine if it is possible to modify the project design to prevent or minimise excess soil generation.

Coastal Acid Sulfate Soils Screening

The Coastal Acid Sulfate Soils screening process assesses the likelihood of Coastal Acid Sulfate Soils being present at a site where a project is proposed (i.e. site is within Probable Coastal Acid Sulfate Soils area) and whether Coastal Acid Sulfate Soils will be disturbed (high risk activity).

The screening process involves undertaking a desktop assessment of available information about the project site to determine whether high risk activity is proposed in a probable Coastal Acid Sulfate Soils area.

A Coastal Acid Sulfate Soils risk area is an area where:

Acid sulfate soils have been previously identified at or near the site (based on Council records);or

An area identified by mapping (based on map of probable Coastal Acid Sulfate Soils) that has the potential to contain Coastal Acid Sulfate Soils.

APPENDIX A shows a map of probable Coastal Acid Sulfate Soils areas in the City of Melbourne. This map has been developed based on consideration of the:

- Coastal Acid Sulfate Soils GIS data set published by Department of Environment and Primary Industries; and

- Atlas of Australia Acid Sulfate Soils GIS data set published by CSIRO Land & Water.

There are a number steps in the Coastal Acid Sulfate Soils screening process, which are presented in a decision making flow chart provided in Appendix B.

The first step in the Coastal Acid Sulfate Soils screening process is to check for the presence of Coastal Acid Sulfate Soils in the vicinity of the proposed project site by checking: (1) the City of Melbourne records; and (2) the map of Probable Coastal Acid Sulfate Soils.

Where the activity is not in an area of probable Coastal Acid Sulfate Soils, then no further actions regarding Coastal Acid Sulfate Soils need to be undertaken. If records or the map of Probable Coastal Acid Sulfate Soils indicate that the project site is likely to be in an area of probable Coastal Acid Sulfate Soils then the Coastal Acid Sulfate Soils risk associated with the project needs to be further assessed.

The Victorian Best Practice Guidelines for Assessing and Managing Coastal Acid Sulfate Soils identifies high risk activities as:

- Excavating soil/sediment (> 1000 m3);

- Extracting or lowering groundwater;

- Filling land or stockpiling soil (more than 100 m3 with an average depth of at least 0.5 m) over in situ Potential Acid Sulfate Soils (PASS); these activities can force the underlying ASS above the water table at the margins of the added soil or fill;

- Planting of vegetation (crops or plantation) that may potentially lower the water table; and

- Coastal or inshore dredging.

Where Council is proposing a project that includes any of the high risk activities, the risk should be further assessed if excavations are likely to be more than 600mm below the site ground level (bgl).  Where excavations are less than 600 mm bgl, then no further actions regarding Coastal Acid Sulfate Soils needs to be undertaken.

If undertaking a high risk activity and proposed excavation is greater than 600 mm, then Council should engage a consultant with Coastal Acid Sulfate Soils management experience to assess the need to sample and analyse soils for the presence of Coastal Acid Sulfate Soils, to enable offsite disposal or management.  If the consultant recommends that soil sampling is not required then no further actions regarding Coastal Acid Sulfate Soils need to be undertaken.

Where the consultant identifies that soil sampling is required, soils should be sampled and analysed for the presence of Coastal Acid Sulfate Soils. Where required, soil sampling and analysis for Coastal Acid Sulfate Soils could be undertaken in conjunction with sampling for potential contamination (see Soil Sampling, Analysis and Classification). The Environment Protection Authority Publication, Acid Sulfate Soil and Rock, Publication number 655.1, summarises sampling frequencies in relation to off-site disposal of Coastal Acid Sulfate Soils.

If sampling and analysis indicate that Coastal Acid Sulfate Soils is not present then no further actions regarding Coastal Acid Sulfate Soils need to be undertaken.

Where soil sampling indicates that Coastal Acid Sulfate Soils is present:

- Excavated soil must be disposed of at a site approved by Environment Protection Authority; and

- Retained soil must be managed in accordance with the Victorian Best Practice Guidelines for Assessing and Managing Coastal Acid Sulfate Soils.

Where Council has identified that it is not undertaking a high risk activity, then the possibility of retaining or reusing soils on site will need to be evaluated.

If excavated soils are to retained onsite and the site is connected to a natural water body or wetland (e.g. within 50 m), then retained soil will require management in accordance with Victorian Best Practice Guidelines for Assessing & Managing Coastal Acid Sulfate Soils.

Where soils cannot be retained and the volume of soil is less than 30 m3, no further actions regarding Coastal Acid Sulfate Soils need to be undertaken. Where the volume of soil is greater5 than 30 m3, Council should engage a consultant with Coastal Acid Sulfate Soils management experience to assess the need to sample and analyse soils for the presence of Coastal Acid Sulfate Soils to enable offsite disposal or management.

Council Preliminary Screening Process

Council adopted the following preliminary screening process to determine when sampling and analysis of soils will be undertaken.

- If the generation of excess soils cannot be avoided, Council will assess if macadam (a form of potentially contaminated road base) will be excavated, and if so, Council will arrange for in situ sampling and analysis to classify the excess soils.

- If the generation of excess soils cannot be avoided and excavation is to occur in an area where Council believes that there is the potential for contamination to be encountered (based on Council’s knowledge of historical fill use in the area, potentially contaminating historical land uses, or prior analysis of soils) then Council will arrange for in situ sampling and analysis to classify the excess soils.

- Council will then assess the volume of excess soils that will be generated. As outlined below, there are two potential excavation scenarios depending on the volume of soils excavated, and scale of the project:

    - Scenario 1 – Council  has determined macadam will not be excavated, works are not in an area where Council believes the potential for contamination exists, excess soil volume is greater than 30 m3 and project defined as a ‘major or minor project’ by Council; and

    - Scenario 2 - Council has determined macadam will not be excavated, works are not in an area where Council believes the potential for contamination exists and excess soil volume is less than 30 m3.

It is noted that the volume of 30 m3 is a nominal volume, which has been determined by Council as a practical means of ensuring sampling is undertaken for those projects with the greatest potential to have significant cost impacts associated with excess soil disposal. This volume is subject to Council review to assess if it is appropriate, noting the soil sampling, analysis and classification requirements outlined in Environment Protection Authority Publications Soil Sampling (IWRG702). Council will review this trigger volume within 12 months of adopting this Procedure.

If excess soil volume is less than 30 m3 (and Council has determined that no macadam, or works in a potentially contaminated area are proposed), then visual assessment during excavation will be used to determine the potential for contamination. Where contamination is observed, or suspected, sampling and analysis are required to classify the waste prior to disposal. The field card provided in Appendix C is to be used as a guide on how to undertake a visual and olfactory inspection of excess soils for contamination, or Asbestos Containing Material.

If excess soil volume is greater than 30 m3, excess soils will be classified based on the results of sampling and analysis.

Soil Sampling, Analysis and Classification

Soil sampling and classification will be undertaken in accordance with Australian Standard 4482.1, Environment Protection Authority Publications Soil Sampling (‘IWRG702’) and Soil Hazard Categorisation and Management (‘IWRG621’).

Council may engage an Environmental Consultant to assist in soil sampling, analysis and classification.  The classification methodology should take into account the following details:

- Location of the site from which soils will be excavated;

- Volume of soils to be excavated;

- The presence of domains at the site (a domain is an area or layer of material with same probable soil hazard category); and

- The availability of historical representative soil classification data.

Soil classification data from previous infrastructure projects in the vicinity of the site may be considered representative if the soil samples meet the following criteria:

- The samples were collected from the same ‘domain’ (a domain is an area or layer of material with same probable soil hazard category);

- Samples were collected in accordance with Australian Standard 4482.1;

- There is a sufficient number of samples to classify soils for disposal in accordance with Environment Protection Authority Publication IWRG621.

Council may engage an Environmental Consultant to assess if soil classification data from previous projects would be considered ‘representative’.

Major Projects

Major Projects are those that involve:

- Public tendering of Council works;

- Prominent locations with high use or lack of space for stockpiling of soils;

- Generation of excess soils over 200m3 in volume.

Failure to appropriately manage and classify the excess soils during major projects has the potential to result in significant additional project costs and delays. It is therefore necessary for Council to classify soils prior to commencement of works, as part of the project planning and tender preparation.

When planning major projects, Council will consider the amount of excess soil and its contamination status.  Where the quantity and nature of contamination is likely to result in significant additional management and disposal costs, Council will evaluate the feasibility of proceeding with the project.

The process and procedures to be followed for Major Projects are summarised below and the decision making flowchart is provided in Appendix B:

- If no representative soil analytical data is available to classify soils for disposal, Council will arrange for an Environmental Consultant to collect representative soil samples in accordance with the Australian Standard 4482.1 and Environment Protection Authority Publication IWRG702.  Samples should be analysed and classified in accordance with Environment Protection Authority Publication ‘IWRG621’ (copies of which are provided in Appendix D). Where required, soil sampling and analysis for contamination could be undertaken in conjunction with sampling for Coastal Acid Sulfate Soils (see Coastal Acid Sulfate Soils Screening).

- Council will evaluate the potential to collect soil samples for waste classification purposes during other intrusive works (e.g. utility clearance or geotechnical works), as this should save on mobilisation and sampling costs.

- An Environmental Consultant may be required to provide Council with a Waste Classification Report which presents the waste classification and the corresponding soil analytical data.  In engaging the Environmental Consultant for this work, Council will require a report that:

    - Confirms that sampling and analysis have been undertaken in accordance with Australian Standard 4482.1 and Environment Protection Authority Publication IWRG702.

    - Confirms that sufficient samples have been taken in accordance with Environment Protection Authority Publication IWRG702 to enable classification of the specific volume of excess soils in accordance with Environment Protection Authority Publication IWRG621.

    - Includes a summary letter confirming the classification of the excess soil is in accordance with Environment Protection Authority Publication IWRG621, which can be made available to the operator of the facility where the excess soil is to be disposed.

- Council will provide the Environmental Consultant with an estimate of the volume of excess soil made during the planning phase, to assist with the design of a suitable sampling program.

- Council will consider the waste classification results and volume estimates during project planning, budgeting and tender documentation preparation.  Council will make the Consultant’s Report available to contract tenderers.

Minor Projects

Minor Projects are those that do not fall into the major projects category as described above, and therefore carry a lesser risk. It is appropriate for Contractors to manage and classify the excess soils as part of the minor project delivery.

The decision making process and procedures to be followed for Minor Projects are summarised below, and the decision making flowchart is provided in Appendix B:

- If no representative soil analytical data is available to classify soils for disposal, the Contractor should arrange for a an Environmental Consultant to collect representative soil samples in accordance with the Australian Standard 4482.1 and Environment Protection Authority Publication IWRG702. Samples should be analysed and classified in accordance with Environment Protection Authority Publication ‘IWRG621’. Where required, soil sampling and analysis for contamination could be undertaken in conjunction with sampling for Coastal Acid Sulfate Soils (see Coastal Acid Sulfate Soils Screening).

- The Contractor should evaluate the potential to collect soil samples for waste classification purposes during other intrusive works (e.g. utility clearance or geotechnical works), as this should save on mobilisation and sampling costs.

- An Environmental Consultant may be required to provide the Contractor with a Waste Classification Report which presents the waste classification and the corresponding soil analytical data. In engaging the Environmental Consultant for this work, the Contractor will require a report that:

    - Confirms that sampling and analysis have been undertaken in accordance with Australian Standard 4482.1 and Environment Protection Authority Publication IWRG702.

    - Confirms that sufficient samples have been taken in accordance with Environment Protection Authority Publication IWRG702 to enable classification of the specific volume of excess soils in accordance with Environment Protection Authority Publication IWRG621.

    - Includes a summary letter confirming the classification of the excess soil is in accordance with Environment Protection Authority Publication IWRG621, which can be made available to the operator of the facility where the excess soil is to be disposed.

Projects < 30m3

- For projects where the excess soil volume is less than 30 m3 (and Council has determined that no macadam, or works in a potentially contaminated area or probable Coastal Acid Sulfate Soils area are proposed), waste classification of excess soils is to be based on field inspection for evidence of contamination, Coastal Acid Sulfate Soils, or visible Asbestos Containing Material. Soils with evidence of contamination, or suspected of being contaminated or containing Coastal Acid Sulfate Soils, will be sampled and classified prior to disposal. The field card provided in Appendix C is to be used as a guide on how to undertake a visual and olfactory inspection of excess soils for contamination, Coastal Acid Sulfate Soils or Asbestos Containing Material.

## Step 2 - Excavation

The decision making process and procedures to be followed in the excavation step are summarised below, with the decision making flowchart is provided in Appendix B:

Scenario 1

In this scenario, excess soils have been pre-classified prior to commencement of excavation and the procedure includes the following steps:

- The Contractor should consider the waste classification results and, if practical, segregate different domains during excavation works (e.g. asphalt, road base and material of different waste classifications (Category A, Category A, Category C, Coastal Acid Sulfate Soils, Fill Material). Asphalt and road base should be reused or recycled in accordance with the Waste Hierarchy. Solid Inert waste should be disposed to a landfill licensed to accept Solid Inert Waste.

- Oversize material (>100 mm in size), should be screened as far as practicable from soils to enable it to be managed as Fill Material and minimise the volume of soils that require disposal to landfill.

- The Contractor should undertake an inspection of the excess soil for visible Asbestos Containing Material or unexpected contamination or Coastal Acid Sulfate Soils during excavation. The field card provided in Appendix C is to be used as a guide on how to undertake a visual and olfactory inspection of excess soils for contamination, Coastal Acid Sulfate Soils or Asbestos Containing Material.

- If unexpected contamination is encountered, soils with evidence of contamination, Coastal Acid Sulfate Soils or Asbestos Containing Material should be segregated from clean material to the extent practical.

- Contractor should arrange for an Environmental Consultant to collect representative soil samples of this segregated material in accordance with the Australian Standard 4482.1, Environment Protection Authority Publication IWRG702, Environment Protection Authority Publication 655.1 (where Coastal Acid Sulfate Soils is present) and to classify the soil for disposal in accordance with Environment Protection Authority Publication IWRG621 and Environment Protection Authority Publication 655.1.

- The Environmental Consultant should provide the Contractor with a Waste Classification Letter, which presents the waste classification and the corresponding soil analytical data. Prior to disposal or treatment of any soil, the nominated receiver should be contacted to verify that there is sufficient soil quality data for them to accept the classification indicated within the report.

- The procedures for waste transport and disposal are determined by the waste category and are described in the Section 4.3

Scenario 2

In this scenario, the excess soil volume is less than 30 m3 and therefore pre-classification of soils prior to excavation has not been undertaken. The procedure for this scenario includes the following steps:

- The Contractor should undertake an inspection of the excess soil during excavation for visible Asbestos Containing Material, Coastal Acid Sulfate Soils or contamination. The field card provided in Appendix C is to be used as a guide on how to undertake a visual and olfactory inspection of excess soils for contamination, Coastal Acid Sulfate Soils or Asbestos Containing Material.

- Soils with no evidence of contamination, Coastal Acid Sulfate Soils or Asbestos Containing Material should be disposed of as Fill Material.

- Soils with evidence of contamination, Coastal Acid Sulfate Soils or Asbestos Containing Material should be segregated to the extent practical from clean material.

- Contractor should arrange for a suitably trained person such as an Environmental Consultant to collect representative soil samples of this segregated material in accordance with the Australian Standard 4482.1, Environment Protection Authority Publication IWRG702 and/or Environment Protection Authority Publication 655.1 (where Coastal Acid Sulfate Soils is present) and to classify the soil for disposal in accordance with Environment Protection Authority Publication IWRG621.

- The Environmental Consultant should provide the Contractor with a Waste Classification Letter which presents the waste classification and the corresponding soil analytical data. Prior to disposal or treatment of any soil, the nominated receiver should be contacted to verify that there is sufficient soil quality data for them to accept the classification indicated within the report.

The procedures for waste transport and disposal are determined by the waste category and are described in the Section 4.3.

## Step 3 – Disposal

The decision making process and procedures for waste transport and disposal are summarised below and the decision making flowchart is provided in Appendix B:

In summary, soil classified as a Prescribed Industrial Waste must be placed in an appropriately permitted vehicle and transported directly to an appropriately licenced facility for disposal or treatment. Each vehicle load of Prescribed Industrial Waste must be accompanied by an Environment Protection Authority Waste Transport Certificate, in accordance the Environment Protection (Industrial Waste Resource) Regulations 2009.  Soils which do not exceed the Prescribed Industrial Waste thresholds can be disposed of as Fill Material.

Soil classified as waste Coastal Acid Sulfate Soils must be disposed of at a site approved by Environment Protection Authority (EMP or licensed) to accept Coastal Acid Sulfate Soils).

The specific requirements for each waste category are summarised in Table 1 below.

Table 1: Waste – Transport, Storage and Disposal

| Excess Soil Category | Description | Transport Requirements | Disposal Requirements |
| --- | --- | --- | --- |
| Fill Material, Asbestos Containing Material “free” | Reported concentrations are less than ‘contaminant concentrations threshold’ for Fill Material and material contains no visible Asbestos Containing Material | Covered vehicle | May be disposed of as Fill Material, no specific regulatory requirements apply. |
| Waste Coastal Acid Sulfate Soils | Soil, sediment, unconsolidated geological material or disturbed consolidated rock mass containing metal sulfides which exceeds criteria for acid sulfate soils specified in Environment Protection Authority Publication 655.1 | Covered Vehicle | Site approved by Environment Protection Authority (EMP or licensed to accept Coastal Acid Sulfate Soils) |
| Category C Prescribed Industrial Waste (Asbestos Waste) | Reported concentrations are less than ‘contaminant concentrations threshold’ for Fill Material and material contains visible Asbestos Containing Material | Environment Protection Authority Permitted Vehicle and Asbestos Containing Material to be wrapped in two layers of polythene sheeting, sealed with adhesive tape and labelled with the asbestos warning mark (See Environment Protection Authority guidelines IWRG611) | Landfill licenced for acceptance of industrial Asbestos Containing Material (Prescribed Industrial Waste). |
| Category C Prescribed Industrial Waste (contaminated soil and Asbestos Containing Material) | Reported concentrations exceed the ‘contaminant concentrations threshold’ for Fill Material, but are less than the Category C threshold and material contains visible Asbestos Containing Material | Environment Protection Authority Permitted Vehicle and Asbestos Containing Material to be wrapped in two layers of polythene sheeting, sealed with adhesive tape and labelled with the asbestos warning mark (See Environment Protection Authority guidelines IWRG611) | Landfill specifically licenced to accept Category C Prescribed Industrial Waste (including Asbestos Containing Material)10. |
| Category B Prescribed Industrial Waste (contaminated soil) | Reported concentrations exceed the ‘contaminant concentrations threshold’ for Cat C, but are less than the Cat B threshold and material contains no visible Asbestos Containing Material. | Environment Protection Authority Permitted Vehicle | Landfill specifically licenced to accept Category B Prescribed Industrial Waste (SITA landfill, Lyndhurst)10. |
| Category B Prescribed Industrial Waste (contaminated soil and Asbestos Containing Material) | Reported concentrations exceed the ‘contaminant concentrations threshold’ for Cat C, but are less than the Cat B threshold and material contains visible Asbestos Containing Material | Environment Protection Authority Permitted Vehicle and Asbestos Containing Material to be wrapped in two layers of polythene sheeting, sealed with adhesive tape and labelled with the asbestos warning mark (See Environment Protection Authority guidelines IWRG611) | Landfill specifically licenced to accept Category B Prescribed Industrial Waste (including Asbestos Containing Material)10 |
| Category A Prescribed Industrial Waste (contaminated soil) | Reported concentrations exceed the ‘contaminant concentrations threshold’ for Cat B but material contains no visible Asbestos Containing Material. | Environment Protection Authority Permitted Vehicle | Treatment facility licenced to treat Category A Prescribed Industrial Waste |
| Category A Prescribed Industrial Waste (contaminated soil and Asbestos Containing Material) | Reported concentrations exceed ‘contaminant concentrations threshold’ for Cat B and material contains visible Asbestos Containing Material. | Environment Protection Authority Permitted Vehicle and Asbestos Containing Material to be wrapped in two layers of polythene sheeting, sealed with adhesive tape and labelled with the asbestos warning mark (See Environment Protection Authority guidelines IWRG611) | Treatment facility licenced to treat Category A Prescribed Industrial Waste (including Asbestos Containing Material)11 |

### Transport Requirements

All Prescribed Industrial Waste transported to an Environment Protection Authority licenced facility, must be transported in covered vehicles permitted by Environment Protection Authority to transport Prescribed Industrial Waste and be accompanied by Environment Protection Authority Waste Transport Certificates at all times.

### Disposal Requirements

There are a number of additional requirements to be considered for each waste category as outlined below:

Category A Prescribed Industrial Waste

- Facility operator must treat waste to meet disposal specification.

- Facility operator is responsible for ensuring waste meets landfill specification following treatment.

Category B Prescribed Industrial Waste

- Must be disposed of at SITA landfill, Lyndhurst.

- Facility operator is responsible for ensuring waste meets landfill specification.

Category C Prescribed Industrial Waste

- Facility operator is responsible for ensuring waste meets landfill specification.

Waste Coastal Acid Sulfate Soils

- Facility operator is responsible for ensuring waste Coastal Acid Sulfate Soils meets specification.

Fill Material

- May be disposed of as Fill Material, no specific regulatory requirements apply.

### Material Tracking

The Contractor should implement a Material Tracking System which tracks all excess soils and Asbestos Containing Material from the point of generation to treatment or disposal, at a licenced facility. The Material Tracking System must include, as a minimum, the following information:

- Volume of excess soil excavated;

- A record of the inspection of the excess soil during excavation for contamination or visible Asbestos Containing Material which includes:

    - Details of any identified contamination;

    - Details of any visual Asbestos Containing Material identified (if no contamination or Asbestos Containing Material is identified this must also be recorded);

    - Waste classification of the soil (if applicable).

- Soil stockpile (and/or storage container) unique identifier.

- Date excess soil was excavated from each location and subsequently transported to a disposal facility;

- Details of the vehicle transporting the soil to a disposal facility;

- Details of the disposal facility;

- Date the excess soil arrived at the disposal facility;

- Copies of Environment Protection Authority Waste Transport Certificates completed by the disposal facility.

The Contractor must collate and retain all documentation relating to the handling, transport, storage and disposal of excess soil and Asbestos Containing Material, including copies of Environment Protection Authority Waste Transport Certificates completed by the disposal facility.

Council should obtain an updated record of the Material Tracking System from the Contractor on a quarterly basis and should periodically audit the Contractor's Material Tracking System and record keeping.

Council should retain copies of the Material Tracking System and Environment Protection Authority waste transport certificates for a minimum of 2 years following the disposal of waste.

# Implementation plan

## Overview

This Procedure document should be implemented by Council’s Contractors through the development of a project specific Soil Management Plan which clearly demonstrates how project works will be undertaken in accordance with the procedures outlined in this Procedure.

It is proposed that documented procedures consistent with this Procedure be provided as a ‘Tender Document’ with Council’s ‘Requests for Tender’ and that the requirement for the development of a Soil Management Plan be included as a clause in Council’s Contracts with its Contractors. An outline of the general requirements of the Soil Management Plan is provided in Appendix C.

This Procedure should be implemented internally through the provision of a training course to relevant Council personnel.

## Training

The Council’s training course should include, as a minimum, communication of the following items described within this Procedure:

- Background;

- Objectives;

- Scope;

- Victorian Waste Management Statutory Requirements;

- Soil Management Procedures, divided into:

    - Planning, with an emphasis on:

      - Modifying project designs to reduce the volume of excess soils generated;

      - Soil sampling and waste classification requirements; and

      - Implications for project budget and timing.

    - Excavation, with an emphasis on:

      - Field inspection of excess soils for unexpected contamination or Asbestos Containing Material;

    - Disposal, with an emphasis on:

      - Waste transport;

      - Waste Tracking; and

      - Record Keeping.

The Contractor will be responsible for ensuring its personnel and subcontractors receive the appropriate training regarding the requirements of this Procedure, and have the adequate resources and/or materials available to implement these measures. The Contractor’s training course should include training in the items listed above. The Contractor is responsible for maintaining an up-to-date Training Register for its personnel.

## Roles and Responsibilities

The following section outlines the roles and responsibilities for personnel involved in the implementation of this Procedure.

### Council

Council’s responsibilities include:

- Ensure excess soils generated during projects are managed in accordance with relevant Victorian statutory requirements;

- Ensure Contractors undertake project works in accordance with the procedures outlined in this Procedure;

- Providing documented procedures consistent with this Procedure to relevant internal personnel and Contractors involved in the works; and,

- Periodically auditing and monitoring Contractor's compliance with this Procedure, including the inspection of soils for evidence of contamination, Material Tracking System and record keeping.

- Develop and maintain a Register of Known Clean and Contaminated Land.

### Contractor Responsibilities

The Contractor’s responsibilities include:

- Ensuring works are undertaken in accordance with Victorian statutory requirements;

- Ensuring works comply with the guidance and procedures provided in this Procedure;

- Ensuring all personnel and subcontractors involved in the works have received appropriate training in the requirements of this Procedure;

- Providing feedback as necessary to Council on the implementation of this Procedure;

- Obtaining all necessary certificates, permits and approvals to undertake handling, transport, storage and disposal of Prescribed Industrial Waste and Asbestos Containing Material;

- Implementation of a Material Tracking System which tracks all excess soils and Asbestos Containing Material from the point of generation to either a licenced treatment facility or disposal at a licenced facility;

- Collation and maintenance of all documentation relating to the handling, transport, storage and disposal of excess soil and Asbestos Containing Material for a minimum period of 2 years; and,

- Ensuring appropriate personal protective equipment is used consistent with Council’s HSE procedures.

### Environmental Consultant (if required)

If an Environmental Consultant is engaged by Council, or its Contractors, its responsibilities include:

- Undertaking preliminary site investigations and soil sampling, assessment and waste classification, as requested; and

- Assisting with liaison with the Council, Contractors, Environment Protection Authority and other key stakeholders, as requested.

## Procedure Auditing and Monitoring

Council will audit and monitor the Contractor's compliance with this Procedure. Table 2 provides a template for the monitoring and auditing program that should be conducted by Council as part of the implementation of the Procedure.  Frequency of audit and monitoring programs will be on a project-specific basis.

Table 2: Procedure Monitoring Tasks.

| Monitoring Task | Performance Indicator | Meets Performance Indicator Yes - ( /No -( / NA |
| --- | --- | --- |
| Inspect Contractor’s Training Register | Training register demonstrates that all project personnel have received Environmental Training relating to the implementation of this Procedure. | ( |
| Conduct a review of field assessment procedures to assess adequacy of Contactor’s procedures for identifying evidence of potential contamination and Asbestos Containing Material. | Contractor adequately assesses and identifies indicators of potential contamination. | ( |
| Check that soils with evidence of contamination are sampled and subsequently assigned as Category A, B or C Prescribed Industrial Waste, Solid Inert Waste or Fill Material prior to disposal. | Waste classification data available for all potentially contaminated soil. Contractor demonstrates that the sampling rate meets 1 per 25 m3 and a minimum of 3 samples requirement. | ( |
| Check the Project’s Materials Tracking System to ensure the excavation, transport and disposal of all excess soils & Asbestos Containing Material is tracked. | The volume of soil & Asbestos Containing Material excavated and transported correlates with the volume of soil which is disposed at appropriately licenced facilities. | ( |
| Check that all excess soil and Asbestos Containing Material are disposed at appropriately licenced facilities. | Environment Protection Authority Waste Transport Certificates demonstrate that all Prescribed Industrial Waste (including Asbestos Containing Material) is disposed at appropriately licenced facilities. | ( |
| Complaints and Incidents Response Register | All community complaints are recorded, mitigated or managed by the Contractor and recorded in the Complaints and Incidents Response Register. | ( |

## Non-Conformance

Any identified non-conformance with the Procedure must be addressed as soon as is practical. The member of staff and/or Contractor responsible for the non-conformance must be notified immediately of the error and provided with guidance on the method of rectification of the problem, if possible.

Contractors are required to keep a Complaints and Incidents Response Register, stating the nature of the non-conformance and the actions implemented to rectify the problem and make this available to Council on request.

# Procedure review and updates

This version of the Procedure is referenced as EDOCs #8742616. Revisions of the Procedure, if required, will be issued based on changes to the proposed Procedure in response to changes in Victorian Waste Management Statutory requirements or significant logistical changes to the program of works.

# appendices

Coastal Acid Sulfate Soils Map

Soil Management Procedures & Coastal Acid Sulfate Soils Screening Process

Soil Inspection – Field Card

Environment Protection Authority Soil Sampling and Waste Classification Guidelines

# Footnotes

Industrial Waste Resource Guidelines Soil Sampling, Document IWRG702, June 2009, prepared under the same Regulations

Industrial Waste Resource Guidelines Soil Hazard Categorisation and Management, Document IWRG621, June 2009, prepared under the same Regulations

Australian Standard 4482.1, Guide to the sampling and investigation of potentially contaminated soil, Part 1: Non-volatile and semi-volatile compounds.

Industrial Waste Resource Guidelines Asbestos Transport and Disposal, Document IWRG611.1, July 2009, prepared under the same Regulations

Volume determined by Council

It is understood that Council will determine if projects are major or minor based on project programme and budget estimate.

Australian Standard AS4482.1-2005, Guide to investigation and sampling of sites with potentially contaminated soil, Part: Non-volatile and semi-volatile compounds, 2005.

Industrial Waste Resource Guidelines Soil Sampling, Document IWRG702, June 2009, prepared under the same Regulations.

Industrial Waste Resource Guidelines Soil Hazard Categorisation and Management, Document IWRG621, June 2009, prepared under the same Regulations.

If soil is also classified as Coastal Acid Sulfate Soils then it must be disposed of at a facility approved by Environment Protection Authority (EMP or licensed to accept Coastal Acid Sulfate Soils)

Treatment facility should be advised if soil is also Coastal Acid Sulfate Soils

# Text boxes

The minimum sampling rate to classify in-situ or stockpiled soils for offsite disposal is 1 sample per 25 m3 and a minimum of 3 samples.  Sampled soils are categorised based on the highest reported concentration.  Alternatively, the soils may be categorised based on a statistical assessment, provided that sufficient sample data is available (i.e. 10 samples for a soil volume <2,500 m3).

Full details of the soil sampling requirements are provided in Environment Protection Authority Publication Soil Sampling (‘IWRG702’), a copy of which is provided in Appendix D.